## Childcare
Goal 1: Expand Access to Affordable, High-Quality Childcare for Families Across Hendricks County
|  |  |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
| Coalition Development |  | Recruit and form leadership team | send application link | vet and select leadership team. Team in place by March 31
|  |  | Create logo for coalition | Research and hire designer | Logo due by March 14 | Will complete the first week in April
|  |  | Develop strategic plan collateral - digital and print |  | Begin when logo is approved. | Collateral due by April 15
|  |  | Hold Coalition Reveal Event |  |  | Send invitations by April 20 including digital strategic plan | hold event May 20
| Strategy 1 | Status | Year 1 (2025) | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
| Increase the number of childcare programs that accept CCDF vouchers and On My Way (OMW) Pre-K. |  | Tactic 1.1 Collaborate with childcare providers to increase awareness of CCDF and OMW Pre-K acceptance benefits. |  | survey providers to understand enrollment hesitancy - consultant
Tactic 1.1.1 Internally collaborate with the task force
|  |  | Tactic 1.1.2 Encourage providers to share how its working and benefitting their program - showcasing it has become easier |  |  | Collect success stories - consultant
|  |  | Tactic 1.2 Develop communications from the Coalition to childcare providers to promote enrollment in these programs. |  |  |  | Use survey results and success stories to develop communications. Tied to 1.1 and 1.1.2
Tactic 1.2.1 Consistent provider engagement with calls, events and communication
Tactic 1.3 Launch a targeted marketing campaign aimed at educating families about the availability of CCDF and OMW Pre-K programs, highlighting eligibility, benefits, and the application process.
| Strategy 2 | Status | Year 1 | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
| Advocate for increased funding and flexible zoning regulations for family childcare. |  | Tactic 2.1 Identify trusted members of the community to bring partners in
Tactic 2.2 Engage policymakers and local business leaders in discussions about expanding childcare funding.
Tactic 2.2.1 Knowing the planning meeting schedules
Tactic 2.2.2 Request to be included in a meeting (or on the agenda) to better share information about the Coalitions work to expand childcare options
Tactic 2.2.3 Utilize the meetings to share what the Coalition is doing
Tactic 2.2.4 Invite policy makers who are interested in learning more about childcare initiatives to the Coalition's meetings
Tactic 2.3 Collaborate with local zoning boards to explore more flexible zoning options for home-based childcare programs.
Tactic 2.4 Engaging neighborhood groups and HOA to help them understand the benefits to having family childcare
Tactic 2.5 Schedule a meeting, being mindful of their time availability, with family childcare providers
| Strategy 3 | Status | Year 1 | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
| Expand access to Level 3 or 4 childcare programs with weekend and evening programming. |  | Tactic 3.1 Identify existing providers willing to expand service hours and support their efforts through community partnerships. | Sylvia and Alicia - Danville tour of the town | Chamber connections - buildings are difficult to find in order to expand |  | Survey providers during provider fair |  |  | Survey providers during provider fair
|  |  | Tactic 3.1.1 Conduct a survey to assess the need |  | Mollie will speak with family engagement specialists to track evening and weekend needs | survey to be part of consultant work
Tactic 3.2 Explore potential grants or funding sources to help cover the costs of extended hours for childcare centers.
Tactic 3.3 Develop and implement an incentive program to encourage childcare providers to offer evening and weekend services
|  |  | Tactic 3.4 Increase the number of trained/prepared childcare professionals |  | Create plan to connect with career center/high schools/alternative schools Sylvia and Dana spoke with Area 31 - check with Chris (are we aware of the job fair on April 30 at BD) | connect with career center/high schools to promote profession - are there ECE specific job fairs at the schools |  | Began stackable credential discussions
Tactic 3.4.1 Identify providers to participate in training
|  |  | Tactic 3.4.2 Develop a pool of substitute teachers | Reach out to Jennifer Myers, Monroe County Smart Start - Jackie
Tactic 3.5 Increase the number of providers at Level 3 or Level 4

## Housing
|  |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Coalition Development |  | Recruit and form leadership team | send application link | vet and select leadership team. Team in place by March 31
|  | Create logo for coalition | Research and hire designer - sent inquiry 3/18 - meeting scheduled for 3/21 | Logo due by March 14 - revised to April 1
|  | Develop strategic plan collateral - digital and print |  | Begin when logo is approved. | Collateral due by April 15
|  | Hold Coalition Reveal Event |  |  | Send invitations by April 20 including digital strategic plan | hold event
Strategy 1 | Status | Year 1 (2025) | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Create a countywide organization that brings stakeholders together and moves to action, including marketing efforts. |  | Tactic 1.1 Convene a task force of housing developers, community leaders, and local government officials to form a countywide housing organization. | Isolate topic to focus on housing production, identify people to participate in smaller subgroup
|  | Tactic 1.1.1 Recruiting for any gap we see in the task force | Ask prior task force attendees to connect us with their networks. Tie to 2.1 Tracy - sent 3/18
| Target Year 2 | Tactic 1.2 Develop a marketing campaign to raise awareness of housing needs and promote the coalition's work, focusing on community engagement.
Tactic 1.2.1 Secure and designate funds/ people for the marketing campaign
Tactic 1.2.2 Social media as a medium to promote the marketing campaign and foster conversation
|  | Tactic 1.3 Organize quarterly meetings with key stakeholders to maintain momentum and ensure alignment of efforts across sectors. |  | recruit organizers to plan symposium series tied to 1.1. Sue and Chris will help. | begin organizing June symposium, set agenda, invite lived-experience speaker, invite subject matter speaker. Identify successes - what works and what doesn't work. 3-5 minute presentation on success stories, how they did it, what was the timeline. come up with 3-5 prompt questions. 1) What obstacles did you successfully overcome and how? 2) Who lives in your homes? 3) Where does funding come from for these projects? 4) What actions have you taken to improve public image around attainable or workforce housing? (keep the tie in with government policy in our pocket for a future symposium date) 5) What would you like town officials to know? To do's-create agenda (Tracy), gather names/contacts to invite (everyone, Tracy will create a Google doc for everyone to put their contacts), personal pitch to your contacts followed by formal invitation from the Coalition. | Send formal invitation on May 5 | Hold quarterly symposium June 24,4:00-6:00 hybrid |  |  | Hold quarterly symposium - elected official focus |  |  | Hold quarterly symposium - connecting economic development and chambers
Tactic 1.3.1 Schedule meetings that are at a variety of times to ensure key stakeholders can attend
Strategy 2 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Increase political and governmental support to advance affordable housing initiatives. |  | Tactic 2.1 Collaborate with local, state, and federal agencies to secure funding for affordable housing projects. |  | Provide a forum where citizens, developers, and town officials can discuss how to make housing more affordable.
Tactic 2.1.1 Find out what funds are available and which funds have extra money
Tactic 2.2 Convene like-minded entities, including housing nonprofits and advocates, to collectively advocate for policy changes and funding at the legislative level.
Tactic 2.2.1 Research and compile problematic pieces of code i.e.) landlord leases/ leasing practices
|  | Tactic 2.2.2 Educate stakeholders based on the research and discriminatory practices | follow and comment on HB1662 State & Local Policies on Homelessness https://iga.in.gov/legislative/2025/bills https://iga.in.gov/information/find-legislators
|  | Tactic 2.3 Share success stories from other communities to demonstrate the positive impact of affordable housing and build political will. |  | attend Grassroots Community Housing Summit March 21 Keep an eye out for symposium series speakers https://www.indymultifaith.org/grassroots-housing-summit-2025 |  |  | Strong Towns conference -Scott and Sue Walton https://gathering.strongtowns.org/ | report out best practices of Strong Towns conference
Tactic 2.4 Collect inventory of current community leaders who have a passion for this topic i.e. utilizing chambers to gain this information
Strategy 3 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Encourage the renovation and repurposing of substandard existing housing. |  | Tactic 3.1 Develop partnerships with local contractors, builders, and real estate investors to renovate and improve substandard housing units.
Tactic 3.2 Advocate for the creation of tax incentives or grants for property owners to renovate or repurpose older housing stock for affordable housing.
Tactic 3.3 Launch a public-private initiative to identify and target neighborhoods with high concentrations of substandard housing for revitalization efforts.
Tactic 3.4 Promote additional infill housing and increase density
Tactic 3.4.1 Advocate zoning in the community i.e.) redesign larger units to accomodate more housing

## Transportation
Goal 3: Expand Access to Transportation for Individuals in Hendricks County
|  |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Coalition Development |  | Recruit and form leadership team | send application link | vet and select leadership team. Team in place by March 31
|  | Create logo for coalition | Research and hire designer | Logo due by March 14
|  | Develop strategic plan collateral - digital and print |  | Begin when logo is approved. | Collateral due by April 15
|  | Hold Coalition Reveal Event |  |  | Send invitations by April 20 including digital strategic plan | hold event May 20
Strategy 1 | Status | Year 1 (2025) | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Fund and execute a transit plan for Hendricks County. |  | Tactic 1.1 Conduct a survey or community engagement process to identify the most critical areas in need of transit services. |  |  | Develop basic framework of a survey. Monica | Discuss with funder who they might recommend as consultants to assist with survey.
| Year 2 - 2nd quarter | Tactic 1.2 Develop a comprehensive transit plan that addresses the needs of key workforce areas.
|  | Tactic 1.3 Identify funding sources and partners to implement the transit plan. | Chase/Tracy to contact HCCF regarding which fund would be appropriate. | Apply for HCCF grants.
|  | Tactic 1.3.1 Identify champions for this cause to include them in this process. | Reach out to Shane Sommers - Chase | Reach out to Robert Pope and Cindy Homan- Tracy/Chase. | Reach out to town council to restart conversation - Mark | Reach out to Senator Clark - Mark will set it up. Include Monica and Tracy
Strategy 2 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Influence regulatory challenges at federal, state, and local levels. |  | Tactic 2.1 Monitor transportation-related legislation and advocate for regulatory changes that benefit the local workforce and entire community.
Tactic 2.2 Invite representatives and influencial decision-makers from local municipalities to join our coalition and reduce barriers to transportation solutions.
Tactic 2.2.1 Explore where childcare and housing workforce barriers intersect with transportation
|  | Tactic 2.3 Host forums with local, state, and federal officials to discuss transportation issues | [5 empty] | Set up mini-symposium with influencers
|  | Tactic 2.4 Connect with similar counties and cities who have gone through the transportation issues process and have successfully implemented transit plans that may be applicable to what we need |  | Circle back to the resources Mark sent previously - Tracy
Strategy 3 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Raise awareness of existing transportation programs, such as ride-share services. |  | Tactic 3.1 Create a public awareness campaign to educate the community about existing ride-share and public transit options.
|  | Tactic 3.1.1 Use storytelling to share benefits of transit, safety measures and other aspects of the workforce. | [5 empty] | connected to Coalition strategy - fair
Tactic 3.2 Partner with ride-share companies to promote discounted services for low-income workers.
Tactic 3.3 Integrate transportation options into local job readiness programs
Tactic 3.4 Offer transportation navigation apps or toolkits
Strategy 4 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Collaborate with employers to invest in transportation solutions for employees. |  | Tactic 4.1 Work with local employers to create incentives for ride-sharing, public transit, or employer-provided transportation.
Tactic 4.2 Establish a fund to help subsidize transportation costs for workers commuting from outside Hendricks County.
Tactic 4.3 Organize a "transportation summit" for employers (a summit or roundtable where employers can learn about transportation solutions, share best practices, and discuss ways to collaborate on improving access to transportation for their employees)
Tactic 4.3.1 Provide employers with potential solutions for transportation challenges based on data

## Coalition
Goal 4: Develop Sustainable Funding Options for the Coalition
|  |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Coalition Development |  | Recruit and form leadership team | send application link | vet and select leadership team. Team in place by March 31
|  | Create logo for coalition | Research and hire designer | Logo due by March 14
|  | Develop strategic plan collateral - digital and print |  | Begin when logo is approved. | Collateral due by April 15
|  | Hold Coalition Reveal Event |  |  | Send invitations by April 20 including digital strategic plan | hold event
Strategy 1 | Status | Year 1 (2025) | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Create a compelling case for supporting the Coalition. |  | Tactic 1.1 Survey Coalition members to create a skills inventory
Tactic 1.2 Develop a comprehensive budget for the Coalition, outlining operational needs and potential impacts.
Tactic 1.2.1 Establish a small team to develop and monitor a budget.
|  | Tactic 1.3 Gather and share stories from individuals and families who have benefited from workforce development programs in the county. | Reach out to Steve and Jerry - Tracy |  |  |  | participate in county fair
Tactic 1.4 Conduct an analysis to demonstrate the ROI of workforce development programs supported by the Coalition
Tactic 1.5 Create a comprehensive communication plan
Strategy 2 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Generate buy-in from key stakeholders. |  | Tactic 2.1 Create a process for identifying and tracking stakeholders
Tactic 2.2 Develop a network of champions, including policy-makers, business leaders, and community members, to advocate for workforce development.
Tactic 2.3 Ensure individuals with lived experience are included in the decision-making process, emphasizing the real-world impact of the Coalition's work.
Tactic 2.4 Tailor presentations about the Coalition's work to specific stakeholders, addressing their unique concerns and demonstrating how the Coalition aligns with their values or objectives
Tactic 2.5 Develop a recognition program that publicly acknowledges key stakeholders—such as policymakers, business leaders, or community members—who actively support the Coalition
Strategy 3 | Status |  | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Build relationships with potential funders. |  | Tactic 3.1 Engage foundations, local businesses, and philanthropic organizations to establish long-term funding partnerships.
Tactic 3.1.1 Leverage our Coalition members to engage their contacts
Tactic 3.2 Host events and roundtable discussions to showcase the Coalition's work and attract new supporters.
Tactic 3.3 Create an inventory of potential funders
Tactic 3.4 Create a sponsorship program with multiple giving levels for businesses and individuals, offering specific benefits for each tier (e.g., recognition at events, website logos, special updates)